## 1 Approval -Roles-Instructions
2018 Digital Business Case Workbook v7-9F
Business Case: |  |  | Core Experience-Enhance Service Orders
Date Approved:
Digital Director Approval:
Business Line Approval:
List all applicable names
The 2018 Digital Business Case workbook has been expanded to include both Digital and Business Line before and after project go-live financial estimates. High Level Risk classification and Value Realization information have also been added. The Business Case is considered a "Living" document.
Roles in Business Case Development (Owners)
Business Line Sponsor: |  | Evaluates the Business Case for accurate and complete representation of all factors related to the accomplishment of the projects business objectives. Directs the activity of the Business Line Contact
Business Line Contact: |  | Supports the development all business line requirements, O&M costs estimates, benefit estimates, high level schedule estimates, assumptions, risks, value realization metrics, and project Success Factors. Completes the business case workbook in collaboration with Digital Director and other SMEs as needed
Digital Lead/Director: |  | Drives business case development with Business Line owners. Directs the gathering and development of all requirements, costs estimates, high level schedule estimates, assumptions, risks and Digital Value Realization metrics and information. Provides final quality review of entire Business Case before submission to Business Line Sponsor. Conducts post go-live assessment of value realization no later than 1 year after project completion.
Digital Contact: |  | Under guidance of Digital Director, gathers and completes all business case workbook requirements, costs estimates, benefit estimates, high level schedule estimates, assumptions, risks, value realization metrics information. Completes the business case workbook in collaboration with Digital Director and other SMEs as needed. Ensures all project documents are version control retained in the Document Repository system of record - The Portfolio Channel of the Demand Planning Team sites.
Roles in Business Case Development (SMEs consulted)
Digital PMO Portfolio Leads |  | Consulted as needed to assess Business Case overall quality. All Business cases will be assigned to one of the Portfolio Leads for review prior to final approval.
Digital Project Manager |  | Consulted to provide quality checks on estimates based upon prior similar project when data is available. This may or may not be the assigned Project Manager. Project Manager assignments occur at Charter Signature stage of Initiation Phase.
BL and Digital BPS |  | Consulted as needed to provide current and historical costs information
General Instructions
1 | Review Entire workbook to plan information gathering requirements and team members. Complete as much of the Business Case as you can with what you know today without any additional work.
2 | Schedule kickoff with BL and Digital Team members to review data and information needs, due dates and assignments. Use first draft to see the gap you need to close to create the information you need to get a successful decision.
3 | Lay out weekly plan, checkpoints, needed to meet Digital Planning dates. Make assignments to team members. If meaningful data cannot be obtained by third week in July (long lead time RFI/RFP or other factors) then agree with BL on timeline when the necessary level of confidence will be achieved.
4 | Business Cases are "Living" project documents. Keep the Business Case current as information is developed. Use standard estimating techniques. If new estimating techniques need to be developed, coordinate with your Portfolio Manager Lead.
5 | Edit the workbook in Excel Online. Share links rather than attach and send files. Cell titles do not display correctly in some cases, but this does not affect data entry.
6 | Our Digital strategy is to not print materials, however, if you need to print, the workbook is formatted. Open the file in native Excel to print tab or entire workbook. The Excel Online print does not recognize the formatting.
7 | Meet with your project sponsors and establish the acceptable confidence level of the data they need to support their decisions and if you have multiple projects, the priority for business case completion for each project.
8 | Data Validation drop-down lists are utilized where practical, have (Select) in title in red, all other fields are text, date or numeric
9 | All Business Cases should be housed in The Portfolio Channel of the Demand Planning Team sites
10 | If you are not clear on next steps, contact your Demand Management Coordinator for support.

## 2 Project Definition
Digital Business Case Project Definition | [6 empty] | Alignment to Ameren Digital Strategy
Project Name |  |  | Prepared by | Date Prepared | Document Repository | Project ID | 1. Hoshin Pillar (Select) | Rationale for Project Alignment
Core Experience-Enhance Service Orders |  |  | Jeronica Jenkins |  |  | Cust-0002 | Digitize | <Some projects drive multiple Pillars or HLOs…select the most important strategic intent of this project>
The Enhanced Service Order Product team will drive digital customer engagement, enhance the customer experience, optimize operational efficiencies and increase customer affordability associated to Ameren's service order processes
Business Case Team
Business Case Owners |  |  |  | Resources Consulted Only For Business Case |  |  | 2. High Level Objective (Select)
BL Sponsor(s) | BL Contact | Digital Lead/Director (Select) | Digital Contact | Digital Portfolio Lead (Select) | Digital PM | Digital & BL BPS (list) | Omni – Channel Customer Experience
T. Oglesby, S. Wiseman | K. Lovett, D. Jacobs | Rajan, Sam | S. Rajan | Eric Robinson | Amanda Humphrey
Set Up and Governance
Expected Delivery Methodology (Select: Agile, Iterative, Waterfall) | CPOC/SLPOC Project (If Yes, Enter Number) | Compliance Project? (If yes, Select Source) | Asset Corp(s) (Select) | Asset Life (Select) | Asset Retirement (if yes, enter net book value) (000s) | R&D Tax Credit Eligible? (Select Y/N) | Investment Portfolio (Select) | Cloud Solution (Select Y/N) | Primary Value Driver by AMO, AIC, AMS/ITC (Select) | Estimated Undivided Joint Interest (Software) (Enter % for each, must total 100%
Agile |  |  | AMO and AIC |  |  |  | Customer | Yes | Financial / Productivity | AMO | 40%
[9 empty] | Financial / Productivity | AIC | 60%
Project High Level Schedule Assumptions |  |  |  | Confidence in Data/Information | Program Managment |  | Business Case Status | Work Orders List (after approval) |  | AMS/ITC
Preferred Start Date | Estimated Duration (in months) | Est In Service Date | Estimated Completion Date | Confidence (Select H, M, L) | Is this a Program or Stand-alone Project? |  | Status (Select) |  |  | Total | 100%
2019-01-01 | 36 | 2021-12-31 | 2021-11-30 | Medium - Similar/Historical Project | Program |  | In Development
Define Project/Background /Objectives/ Benefits
<Provide the reasons why the project or business change has come about and state the problem, opportunity or change of circumstances. Using SMART Goals format: State the specific business objectives for the program/project. If the objectives are achieved, what are the expected benefits to the business? Benefits are typically described in business terms and these ideas should be evident in Tab 3 Financials - Net Business Value.
NEW - Establish a new Service order Agile team and deliver an expectional move / service order experience that allows customers to self-service . Includes estimated cap costs associated to the Platform team who will aid the digital teams in their delivery capabilities, quality and speed.DK- For estimates include awareness of AMI related functionality and IL pending enhancements to align service orders. KS - [‎06/‎25/‎2018 9:10 AM] Haller, Timm R: 1125003 - RCD - Order Data Availability Enhancements from the Business - PCR #136
Project Outcomes/Deliverables
<Describe the Project Deliverables and Outcomes that result from the work. Outcomes are typically describe in operational terms such as lower call volume, few truck rolls…these are quantifiable non-financial metrics. These ideas or descriptions should be translated into specific metrics and listed on Tab 4 Value Realization.
1. Increased productivity for both contact center and field employees related to all deflection 2. Increased customer satisfaction as measured by FOCUS and Ameren Listens field surveys 3. Decreased customer effort in establishing or canceling service 4. Partnerships with companies to provide customers with energy usage information before starting service (i.e. Realtor.com, Zillow, etc.) 5. Enhanced mobile web experience when starting, stopping or transferring service 6. Enhanced customer experience with other service orders identified in journey mapping
Scope: In Scope and Out of Scope/High-level Requirements | [6 empty] | Alternatives Considered
<Describe what is included and what is excluded from the project for both Business Lines and Digital work…be exhaustive to the extent known at this time> | [6 empty] | List alternatives considered and summarize why this project was determined most effective solution.
In Scope: • Explore and implement new and/or optimize service order processes specific to two journeys: Start, Stop and Transfer Service. • Identify drivers of customer satisfaction and create actionable voice of the customer metrics for Start, Stop and Transfer Service. • Define the MVP for Start, Stop and Transfer Service. • Establish a backlog of user stories that the enhanced service order team will use to deliver the initial release for the MVP and for future releases. • Develop KPIs and metrics to track the impact of the MVP
High-level Risk Assessment |  |  |  |  | Risk Rating | Notes: Prerequisites, Interdependencies, Resources, Risks
< List the top 3 Risks to successful business outcome / project outcome achievement and rate risk High, Medium or Low impact…Add explanation to Prerequisites, Interdependencies, Risks Notes > |  |  |  |  | Select: High, Medium, Low | <Provide prerequisites and conditions required to fulfill this project, as well as possible dependencies or implications for other projects or systems that may impact this or other projects. List Sourcing and Resource constraints or challenges and nature of the issue. If you have a High Risk, provide notes on why the risk is High>
1 | System dependencies such as ADMS, OAS, CSS and Ameren.com |  |  |  | High | Other teams using the same systems may have higher priorities and cause delays for the Enhanced Service Order team product delivery. Resources should be full-time and solely dedicated to the team. The use of part-time resources causes delays in product delivery. Vendor should be held accountable for estimated delivery dates. Vendors should also be responsible for ensuring they have full requirements/analysis and capacity to complete work before accepting bids.
2 | Resource constraints |  |  |  | High
3 | Vendor dependencies |  |  |  | High

## 3 Financials
Summary Financials
|  |  |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023
Comments
|  | Total Digital Benefits |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Total Business Line Benefits |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Net Business Benefits (Digital + BL) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Total Project Investment Costs (Capital + Project O&M) |  | 3428 |  | 3649.2191 |  | 3649.2191 |  | 3549.2191 |  | 0
|  | Net Value after Project Costs |  | -3428 |  | -3649.2191 |  | -3649.2191 |  | -3549.2191 |  | 0
|  |  | Treasury Corp WACC as of June 2018 | 6.12%
|  |  | NPV | -12322.9481 |  | Calculated on Net Value after Project Costs
Estimated Funding Source
|  |  |  | AMO |  | AIC |  | ITC |  | AMS |  | Total
|  |  | Year | 40% |  | 60% | [5 empty] | 100% |  | Enter %s to fill table
|  |  |  | Cap | O&M | Cap | O&M | Cap | O&M | Cap | O&M
|  |  | 2019 | 1331.2 | 40 | 1996.8 | 60 | 0 | 0 | 0 | 0
|  |  | 2020 | 1419.6876 | 40 | 2129.5315 | 60 | 0 | 0 | 0 | 0
|  |  | 2021 | 1419.6876 | 40 | 2129.5315 | 60 | 0 | 0 | 0 | 0
|  |  | 2022 | 1419.6876 | 0 | 2129.5315 | 0 | 0 | 0 | 0 | 0
|  |  | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 5590.2629 | 120 | 8385.3944 | 180 | 0 | 0 | 0 | 0
Project Financials
|  | Business Case |  | Financial Impact ($000)
|  |  |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023
|  | Opportunity Overview Reference Data Only |  | 3300 | 500 | 3300 | 500 | 3300 | 500 | 3300 | 0 | 0 | 0
|  | Enter Costs as Positives (000s) | RT | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M | Comments
IMPLEMENTATION COSTS | D | Labor - Bus Line | LM/LU | 955 |  | 955 |  | 955 |  | 955 |  |  |  | Sprint Zero = O&M Cost (refer to notes for total spend for labor cost)
| D | Labor - IT | LM/LU | 1300 |  | 1300 |  | 1300 |  | 1300 |  |  |  | Sprint Zero = O&M Cost (refer to notes for total spend for labor cost)
| D | Project Management | LM/LU/EC/ET | 70 |  | 70 |  | 70 |  | 70 |  |  |  | PM Consultant
| D | Scheduler | LM/LU/EC/ET
| D | Organizational Change Mgmt. | LM |  | 20 |  | 20 |  | 20 |  |  |  |  | Corp Comm releases and materials
| D | Consulting Services - SOW | EC | 550 |  | 550 |  | 550 |  | 550 |  |  |  | "Agile" Coach consulting firm & the Accenture Platform Team; moved $200k from O&M to Capital for vendor work
| D | Consulting Services - Staff Aug | ET
| D | Managed Services | EC
D
| D | Software Purchases | BQ
| D | Hardware Purchases | BK
| D | Individual Expenses | 80/82 | 40 |  | 40 |  | 40 |  | 40 |  |  |  | Team travel expenses
| D | Training Development | 80/82 | 50 |  | 50 |  | 50 |  | 50
| D | Training Rollout | 80/82 |  | 80 |  | 80 |  | 80
| D | Post Imp Service Support | LM/LU/EC/ET
| D | Other (Describe)
| D | Contingency | CT | 276 |  | 276 |  | 276 |  | 276
| Total Implementation Costs |  |  | 3241 | 100 | 3241 | 100 | 3241 | 100 | 3241 | 0 | 0 | 0
| Indirect Overhead** |  | 4% | 0 |  | 129.64 |  | 129.64 |  | 129.64 |  | 0 |  | **Only IT Finance is authorized to fill Indirect Overhead & AFUDC
| (Ave of expected 2019 and 2020) AFUDC** |  | 5.51% | 87 |  | 178.5791 |  | 178.5791 |  | 178.5791 |  | 0
| Total Project Investment Costs |  |  | 3328 | 100 | 3549.2191 | 100 | 3549.2191 | 100 | 3549.2191 | 0 | 0 | 0
|  |  |  | 3428 |  | 3649.2191 |  | 3649.2191 |  | 3549.2191 |  | 0
Digital and Business Line - Outcome Benefit Financials
Current Digital Operational Costs
Enter Costs as positives (000s) |  |  |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | Comments
|  |  |  | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M
Current Digital Costs | D | License Fee
| D | Annual Software Maintenance
| D | Annual Hardware Maintenance
| D | Training
| D | Other 1
| D | Other 2
| D | Other 3
| D | Other 4
|  | Total Annual Current Costs |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Digital Operational Costs after Project Go-Live
Enter Costs as positives (000s) |  |  |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | Comments
|  |  |  | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M
Proposed Digital Costs | D | License Fee
| D | Annual Software Maintenance
| D | Annual Hardware Maintenance
| D | Training
| D | Other 1
| D | Other 2
| D | Other 3
| D | Other 4
|  | Total Annual Costs after Project Go-Live |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Total Annual Digital Benefits=Total Annual Current Costs - Total Annual Costs after Go-Live |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Digital Annual Benefits are positive when ongoing costs are reduced and negative when they increase from current costs
Current Business Line Operational Costs
Enter Costs as positives (000s) |  |  |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | Comments
|  |  |  | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M
Current BL Costs | BL | Reduction of inbound calls to advisors | [11 empty] | Being able to complete the request online or via the IVR will help shift customers to self-serve thereyby calling us less - call deflection savings will be determined by October 2018
| BL | Reduction of customer interaction with CSR via Inbound Phone, Email, Chat | [11 empty] | Increased self service options with reduced customer effort will result in fewer Customer interactions with CSRs
BL
| BL | Example D
| BL | BL Other 1
| BL | BL Other 2
| BL | BL Other 3
| BL | BL Other 4
|  | Total Annual Current BL Costs |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Business Line Operational Costs after Project Go-Live
Enter Costs as positives (000s) |  |  |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | Comments
|  |  |  | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M | Capital | O&M
Proposed BL Costs | BL | Reduction of inbound calls to advisors
| BL | Reduction of customer interaction with CSR via Inbound Phone, Email, Chat
| BL | 0
| BL | Example D
| BL | BL Other 1
| BL | BL Other 2
| BL | BL Other 3
| BL | BL Other 4
|  | Total Annual BL Costs after Project Go-Live |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Total Annual BL Benefits=Total Annual Current BL Costs - Total Annual BL Costs after Go-Live |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Business Line Annual Benefits are positive when ongoing costs are reduced and negative when they increase from current costs

## 4 Value Realization
Value Realization Management
Value Realization management is the process of measuring Capital and O&M investment performance based upon achieving both Business Objectives and Project Success Criteria. Business Line Project Sponsors, Business Line Contacts, Digital Directors and Digital Contacts work together to establish SMART Business Objectives and Project Success Criteria during the initiation phase (Opportunity Overview and prioritization, Business Case and Charter) and are responsible for evaluation of actual performance against Business Case estimates. Digital Directors will conduct Value Realization assessments no later than 1 year after project completion.
Financial Benefit Metrics
Address each benefit value from the Financial sections with a metric that will enable benefit tracking post project completion
|  | Benefit Statements (Source: Pre-populated from Tab 3 Financials) | Metric that Demonstrates Impact | System/Source for Metric Data | Baseline Metric Value as of Business Case Date | Estimated Value 1 Yr. after Project Completion Date | Notes, Assumptions, Calculations
1 | Digital | License Fee
2 |  | Annual Software Maintenance
3 |  | Annual Hardware Maintenance
4 |  | Training
5 |  | Other 1
6 |  | Other 2
7 |  | Other 3
8 |  | Other 4
9 | Business Line | Reduction of inbound calls to advisors |  |  |  |  | Being able to complete the request online or via the IVR will help shift customers to self-serve thereyby calling us less.
10 |  | Reduction of customer interaction with CSR via Inbound Phone, Email, Chat |  |  |  |  | Increased self service options with reduced customer effort will result in fewer Customer interactions with CSRs
11 |  | 0
12 |  | Example D
13 |  | BL Other 1
14 |  | BL Other 2
15 |  | BL Other 3
16 |  | BL Other 4
Non-Financial Benefit Metrics
These measure critical elements of business strategy, are quantifiable, but do not have a financial valuation
|  | Other Operations Metrics or value described in Tab 2 Project Description or in Opportunity Overviews | Metric that Demonstrates Impact (e.g. CSI, SAIFI,VPQ etc.) | System/Source for Metric Data | Baseline Metric Value as of Business Case Date | Estimated Value 1 Yr. after Project Completion Date | Notes, Assumptions, Calculations
AMO | Cust | Increased transactional overall satisfaction and loyalty | FOCUS |  |  |  | Low effort and time for do start/stop/move seemlessly online or IVR
AMO | Oper | Potential reduction in inbound call volume to advisor | IVR Containment/Advisor Answered Calls |  |  |  | Easier self service
AMO | Cult | Fewer inter-department calls to check status |  |  |  |  | More effective use of time for co-workers
AIC | Cust | Increased transactional overall satisfaction and loyalty |  |  |  |  | Reduction in customer effort and increased self service
AIC | Oper | Reduction in inbound call volume to CSR |  |  |  |  | Reduction of customer effort in self service
AIC | Cult | Reduction in call transfer |  |  |  |  | More effective use of time for co-workers
AMS/ITC | Cust
AMS/ITC | Oper
AMS/ITC | Cult
If additional metric information is needed, use Tab 5 Team Notes-Calcs

## 5 Charter
Notes for Development
Executive Sponsor Summary | [10 empty] | MFN=Master Field Name and indicates the data is in Joe's Master file and will be imported to the charter document.
Project Name | [7 empty] | Project ID
Core Experience-Enhance Service Orders | [7 empty] | Cust-0002
Project Leadership
| Business Line Sponsor | [6 empty] | Business Line Contact
| T. Oglesby, S. Wiseman | [6 empty] | K. Lovett, D. Jacobs
| Digital Director | [6 empty] | Digital Contact
| Rajan, Sam | [6 empty] | S. Rajan
| Digital PMO Lead | [6 empty] | Digital Project Manager (Execution) |  |  | The Charter document should have the PM who is actually going to execute the project - the BC PM is an advisor. They can be the same resource
Eric Robinson
Estimated Project Costs (000s)
|  | AMO |  | AIC |  |  | ITC |  | AMS
% |  | 40% |  | 60% |  |  | 0% |  | 0%
Year |  | Cap | O&M | Cap | O&M |  | Cap | O&M | Cap | O&M
2019 |  | 1331.2 | 40 | 1996.8 | 60 |  | 0 | 0 | 0 | 0 | This table reflects what is in the business case summary
2020 |  | 1419.6876 | 40 | 2129.5315 | 60 |  | 0 | 0 | 0 | 0
2021 |  | 1419.6876 | 40 | 2129.5315 | 60 |  | 0 | 0 | 0 | 0
2022 |  | 1419.6876 | 0 | 2129.5315 | 0 |  | 0 | 0 | 0 | 0
2023 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Total |  | 5590.2629 | 120 | 8385.3944 | 180 |  | 0 | 0 | 0 | 0
Estimated Benefit Streams (000s)
|  | 2019 | 2020 | 2021 | 2022 |  | 2023
Digital |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  | This table reflects what is in the business case summary
Business Line |  | 0 | 0 | 0 | 0 |  | 0
Net Benefits |  | 0 | 0 | 0 | 0 |  | 0
High Level Schedule
Start |  | Duration | In Service | Completion | [5 empty] | If applicable:
2019-01-01 |  | 36 | 2021-12-31 | 2021-11-30 |  | NPV | -12322.9481 |  |  | CPOC Code | Missing these fields in the master - would prefer to have them.
Project Background/Objectives/Benefits
NEW - Establish a new Service order Agile team and deliver an expectional move / service order experience that allows customers to self-service . Includes estimated cap costs associated to the Platform team who will aid the digital teams in their delivery capabilities, quality and speed.DK- For estimates include awareness of AMI related functionality and IL pending enhancements to align service orders. KS - [‎06/‎25/‎2018 9:10 AM] Haller, Timm R: 1125003 - RCD - Order Data Availability Enhancements from the Business - PCR #136
Digital Strategy Alignment
Hoshin |  | Digitize |  |  |  |  | HLO | Omni – Channel Customer Experience
Project Scope (In Scope/Out of Scope)
In Scope: • Explore and implement new and/or optimize service order processes specific to two journeys: Start, Stop and Transfer Service. • Identify drivers of customer satisfaction and create actionable voice of the customer metrics for Start, Stop and Transfer Service. • Define the MVP for Start, Stop and Transfer Service. • Establish a backlog of user stories that the enhanced service order team will use to deliver the initial release for the MVP and for future releases. • Develop KPIs and metrics to track the impact of the MVP
Business Primary Impact Areas (Drop Down - Check all that apply) (PM complete)
O& M Savings | [7 empty] | Cost Avoidance |  |  | New fields - we have no way to analyze projects by these factors…would be good to have them for Value Realization - Projects do not have singular impact…we want to know all the impacts. These are all new fields
Business Risk Mitigation | [7 empty] | New Business Capabilities
Digital Risk Mitigation | [7 empty] | Impact to Business Strategy Primarily
Compliance Mitigation | [7 empty] | Other
Project Risks
1 | System dependencies such as ADMS, OAS, CSS and Ameren.com
2 | Resource constraints | [9 empty] | Joe - this should be in MFN.
3 | Vendor dependencies
Project Success Criteria (Drop Down, Rank in Order of Importance) (Primary Sponsor complete) | [12 empty] | Project Success Criteria
Success of this Project will be judged by: | [12 empty] | Achieving Digital Value (Digital Net Benefits)
1 | [10 empty] | All new fields, but will be drop downs to analyze CSFs across portfolio |  | Achieving Business Line Value (Business Line Net Benefits)
2 | [12 empty] | Achieve Scope Requirements (Waterfall)
3 | [12 empty] | Achieving Costs Estimates
4 | [12 empty] | Achieving Estimates for Schedule
5 | [12 empty] | Achieve Highest Value Scope Delivered within Fixed Cost and Schedule (Agile)
6 | [12 empty] | Achieving Quality Control Plan objectives
7 | [12 empty] | Responsiveness/Effective Change Control (Waterfall)
Additional Project Success Criteria (Free form text (Primary Sponsor complete) | [12 empty] | Fostering a Positive Partnership within the Digital and Business Line team
[11 empty] | This is free form text as drop down list cannot be too extensive |  | Effective Organizational Change Management
Effective Stakeholder Management (Keeping stakeholders informed)
Effective User Acceptance Testing (user involvement in solution outcomes)
Timely Resource Acquisition and Onboarding
Effective Project Risk Mitigation
Approval to Proceed with Project - Names and Dates must be manually entered (PM complete)
Business Line Sponsor AMO | [7 empty] | Embed Digital Signature Email Here |  |  |  | How to Embed Approval Emails:
[11 empty] | Digital signatures only - email approvals are imported here - ink and scan not an option | 1. Select the email you want to embed.
Date: (mm/dd/yy) | [10 empty] | Date signed must be manually entered…no way to automate, allows verification through missing data reports | 2. Go to the File tab in Outlook, select "Save As" option and change type to "Outlook message format". Change the file name to "Name_Approval". Execute save to your Desktop or other repository for next step.
Business Line Sponsor AIC | [7 empty] | Embed Digital Signature Email Here
[11 empty] | Multiple sponsor lines are available if needed, but names must be manually entered. | 3. Open Excel Business Case document from Teams. Select "Edit in Excel" drop-down. Once opened, be sure to check for any notices to allow editing. Select Charter tab, scroll down and select the cell where you want to embed the file.
Date: (mm/dd/yy) | [11 empty] | 4. Go to "Insert" and select "Object" option from Excel top ribbon.
Business Line Sponsor ITC | [7 empty] | Embed Digital Signature Email Here
5. In the new window, select the tab at the top "Create from File" and then select your file through the "browse" function to the site where you stored the saved email.
Date: (mm/dd/yy) | [11 empty] | 6. Check the option box "Display as Icon". You can edit the icon text to just "Name Approval" to eliminate path text or if you have renamed the file, just hit enter.
Business Line Sponsor AMS | [7 empty] | Embed Digital Signature Email Here
7. You should see your embeded file in the cell you selected.
Date: (mm/dd/yy) | [11 empty] | 8. Open the object to ensure it is the correct object and that it opens and is legible.
Digital Director/Lead | [7 empty] | Embed Digital Signature Email Here
9. Manually key in the Name of the Approver and the approval date field in prescribed format (to support business case analytics).
Date: (mm/dd/yy) | [10 empty] | same | 10. Save your Business Case document…Excel should write the file back to your Teams SharePoint location. Do not perform Save As.
11. Excel Online cannot display embeded files. The only way to check success is to open the file in native Excel, then the email will be visible.

## 6 Charter Instructions
Charter Instructions |  | Development Note
Roles in Charter Development and Approvals
Business Line Sponsor: | Evaluates the Business Case for accurate and complete representation of all factors related to the accomplishment of the projects business objectives. Directs the activity of the Business Line Contact. Completes the Project Success Criteria. Provides email "Approval Signature" to represent "Project Approval" to proceed with project execution as specified in the Business Case and Charter document.
Digital Lead/Director: | Drives business case development with Business Line Sponsors and Contacts. Directs the gathering and development of all requirements, costs estimates, high level schedule estimates, assumptions, risks and Digital Value Realization metrics and information. Provides final quality review of entire Business Case and Charter before submission to Business Line Sponsor. Monitors value realization. Partners with Business Line sponsor in completing the Project Success Criteria in the Charter Document. Directs Business Line Sponsor and own email Approval Signature (embedded in Charter) to indicate business case approval and authorization to proceed with project into execution phases.
Digital Project Managers | Digital Project Managers support the Digital Director by conducting Quality Control on the Business Case and Charter documents. Through initiation and planning stages of a project life-cycle, regardless of delivery methodology, the PM should keep the business case up to date. When the project passes Gate 3 or Checkpoint 3, the business case should reflect the best known quality information and decisions that have been made about the project. The quality of the Charter will depend directly on the quality of the Business Case.
Overview
This is the stand-alone 2019 Charter document, developed to auto-generate from an existing business case. As much existing information as possible has been pulled forward into the charter. New required information is needed to support portfolio analytics, surveys and metrics. Signatures may only be evidenced through "Approval Emails" being embedded into the designated field at the end of the charter. All new fields are considered mandatory in order to support portfolio analytics and PMO processes.
The signed charter is not a required document to open up a Work Order. The Charter is an important document to evidence project sponsors have seen, reviewed and agree with the business case information (summarized in the Charter) and have provided Project Success Criteria to guide the team during execution and to support post-go-live surveys and Digital metrics. Signed charters are strongly encouraged as part of the Business Line and Digital Partnership. |  | Check wording consistent with other communications regarding WO work flow and requirements
Project Managers steps to take to update Initial Charter - Quality Control
The initial charter will be generated for any Business Case with a Demand Planning status of "In Plan" and "Funded" and placed in the same Team/Portfolio as the Business Case. The Project Manager should review the Initial Charter to identify what data needs to be updated in the Business Case, in particular descriptions and financials. Make sure the charter communicates the most current understanding of the team. PMs should also edit the Digital Project Manager Name field, the CPOC Code field if applicable, and the Business Primary Impact Areas on the Charter file. Editing should be done in Excel Online . Charter data will be pulled into the Master Data file and retained. Once the PM is satisfied with the edits to the business case and Initial Charter, a new charter may be requested. These edits and reviews should be done before engaging the Business Line Sponsor for their review. |  | We do not have a prescribed process for updating the BC and do not have a method to unlock those fields. The fields have been unlocked on a case by cases basis, but this process step will require a global change…TBD
Initial Steps to take with Business Line Sponsor - Complete the Project Success Criteria
The Digital Director and PM should engage Sponsors in a review of the charter, in person or electronically. An email chain should be established, requesting the Sponsors to review the Charter on the team site and to complete the "Project Success Criteria" section. There is only one Charter per business case, so with multiple Sponsors, one must be selected to represent all the sponsors when selecting the Project Success Criteria. The PM should determine and manage the email traffic with multiple sponsors.
Project Success Criteria
Project Success Criteria are stakeholder performance expectations that are within the control of the project team from Business Case Approved Signature stage to Project Close-out and set up for Value Realization. Project Success Criteria reflect how the team performed in conducting the project and becomes the basis for Project Sponsors to assess whether the project was delivered successfully. Project Sponsors/Contacts complete this section prior to Approval. While there are many criteria that teams can and should be evaluated on, select criteria that are most relevant to the nature of the project, the conditions the project is being planned and executed under and what is most important in how the team conducts the work. This charter has a drop down list of success criteria to start with, but also provide a free-form text area to tailor the expectations further. |  | Dave, Cort and Eric need to review the drop down list for adds, changes, deletes….
Request "Approval to Proceed" emails.
The 2019 Charter provides for email-based Approvals only. The Director or PM should send the Charter to the Business Line Sponsor via email with an ask to respond to the email with "Approved To Proceed" or "Additional Information Requested" in the response. When the email is returned with "Approved to Proceed", the Director or PM should follow the directions below to embed the email in the Charter document in the designated location. The instructions are also repeated to the right of form in the Charter tab. The name and signature date must be entered manually as these fields are used for analytics. Charters must reside in the location where the PMO generated them initially in order to facilitate analytics (collocated with Business Case file)
How to Embed Approval Emails:
1. Select the email you want to embed.
2. Go to the File tab in Outlook, select "Save As" option and change type to "Outlook message format". Change the file name to "Name_Approval". Execute save to your Desktop or other repository for next step.
3. Open Excel Business Case document from Teams. Select "Edit in Excel" drop-down. Once opened, be sure to check for any notices to allow editing. Select Charter tab, scroll down and select the cell where you want to embed the file.
4. Go to "Insert" and select "Object" option from Excel top ribbon.
5. In the new window, select the tab at the top "Create from File" and then select your file through the "browse" function to the site where you stored the saved email.
6. Check the option box "Display as Icon". You can edit the icon text to just "Name Approval" to eliminate path text or if you have renamed the file, just hit enter.
7. You should see your embeded file in the cell you selected.
8. Open the object to ensure it is the correct object and that it opens and is legible.
9. Manually key in the Name of the Approver and the approval date field in prescribed format (to support business case analytics).
10. Save your Business Case document…Excel should write the file back to your Teams SharePoint location. Do not perform Save As.
11. Excel Online cannot display embeded files. The only way to check success is to open the file in native Excel, then the email will be visible.

## 7 Team Notes-Calcs
This tab is for any notes that cannot be captured in the input tabs. It may also be used for detailed costing assumptions that then feed Tab 3 Financials.
Notes | 5 Business resources (720k) and 3 part-time resources (185k). IT Labor resources (1.05m). Platform Team (500k)
Calculations

## 8 Guide - Hoshin Selection
How To Think About Classifying Your Project Into Pillars and HLO
This is an evolving draft as teams work with the concepts…additional guidance will be added with practice
Pillar | Digitize | Simplify | Innovate | Culture | Governance
Overall Vision | Provide a best-in-class digital experience to our customers and co-workers to WIN! | Simplify the way we work, make it easier for our customers to do business with us and improve profitability. | Anticipate customer needs and develop new digital solutions in order to deliver sustainable differentiated offerings. | Curate and recruit an admired, sought-after team - excited for our future opportunities, with a bias for action and an agile mindset who will shape the changing marketplace. | Prioritize the most impactful initiatives to our customers and execute to drive value while managing legal, regulatory, cyber and customer risk.
Pillar Clarifying Questions | Does the objective transform the interaction between co-workers, customers, and Ameren as a whole? | Does the objective revolve around improving our daily operations? | Is the project or initiative centered around future capabilities not yet in place? | Is the objective regarding people development, retention, or hiring? | Is an external committee or government office driving the action?
HLO | Omni-channel Customer Experience | Field Worker Transformation | Analytics, Automation, AI | Role Definition and Career Opportunities | Right Investments, Execution, and Value-realization
HLO Clarifying Questions | Does the objective make it easier for customers to interact with Ameren through implementation or enhancements of digital solutions? | Does the objective mobilize and streamline the field co-worker experience? | Does the objective include implementing or exploring digital solutions revolving around analytics, automation, or AI to increase efficiency and effective decision making? | Does the objective center around attracting, retaining, or investing in new or existing digital co-workers and their career paths? | Does the objective involve the process of identifying value-added project investments through effective management to provide clear results?
HLO | Smart Grid Technologies | End-to-End Process Approach | Grid of the Future | Business Alignment | Digital Vendor Management
HLO Clarifying Questions | Does the objective involve implementing customer-facing state-of-the-art grid enabled product and services? | Does the objective enable operational efficiency and continuous improvement across Ameren functions with digital solutions? (Digital supporting business lines) | Does the objective include planning, implementing, or utilizing Intelligrid, DERs, or other emerging Grid of the Future technology to provide modern, competitive offerings? | Does the objective transform and accelerate business processes by allowing Digital to adapt mindsets through education and partnerships? | Does the objective help establish a Vendor Management office to create strategic partnerships, reduce O&M, and ensure effective capital investments?
HLO | Seamless Co-worker Experience | Operations Excellence | Exploring Future Technologies and Capabilities | User-centric Design & Agile | Architecture Standards
HLO Clarifying Questions | Does the objective implement or enhance digital co-worker solutions to provide a mobile, anywhere, anytime experience? | Does the objective include upgrading, maintaining, or optimizing operational efficiency or reducing technical debt within the Digital organization? (Digital supporting Digital) | Is the objective in early research, pilot, or POC phasing of an initiative surrounding emerging, innovative? | Does the objective focus on implementing the agile methodology for better and faster user-centric design? | Does the objective include strengthening architecture standards, definitions and patterns?
HLO |  |  |  | Innovation Center and Talent Pipeline | Cybersecurity and Regulatory Compliance
HLO Clarifying Questions |  |  |  | Does the objective enable Digital to better attract new or collegiate talent by building the brand of Ameren Digital? | Does the objective support proactively managing cybersecurity, regulatory and customer risk? (Includes projects executed to comply with government/social requests)

## 9 Guide - SMART Goals
Guide to SMART Goal Setting
SMART is a simple reminder to answer key business case fields with the most valuable information the team has at the time of completing the form and updating the form as new information becomes available.
S | Specific | Simple, sensible, significant, clearly stated. Try to answer the 5 Ws: What does the project accomplish, Why is the project important, Who is involved, Where is it located, Which resources or limits are involved?
M | Measurable | Meaningful, motivating. Try to answer: How much, How many, how will we know when it is accomplished?
A | Achievable | Agreed, Reasonable, Resourced. A stretch, but attainable. Try to answer: How can we make this project happen? How realistic is the project given what we know?
R | Relevant | Aligned to business strategy. Results-based. Try to answer: How much does this matter to the business? Is this the right time?
T | Time-bound | Time-based, time limited, time/cost limited, timely, time-sensitive. Try to answer: When should we do this? Is there a preferred time to do this project? What is the proper sense of urgency?

## 10 Guide - Typical Risks
Typical Project Risks
Risks include risks under the control of the project team, but also risks in the Business Line where the ultimate business outcomes are expected…think through all the risks, project and business line and list the three most important in the Project Definition tab. The list below is intended to spur thinking and is not intended as a pick list. Be sure to engage Business Case team in effective risk discussion.
| Risk Types | Examples Risk Descriptions
1 | Architecture Review Board (ARB) | Project architecture does not fit desired architectural standards
2 | Clear Roles and Responsibility | Project Roles are not clear or not defined
3 | Communication | There is no budget for Change Management
4 | Contracting | Sourcing will require extensive requirements definition. Long lead time sourcing events required
5 | Cost Benefit Analysis Completed | Business Case is missing key cost drivers
6 | Cyber Security | Cybersecurity related costs are unknown at this time
7 | Estimates | Estimate confidence is low, estimates may be off by 50%
8 | Facilities | Project team will require dedicated co-located facilities and none are available. Consultants require sign-on access and remote location coordination
9 | Finance | This project continues to come up on low investment priority from prior years
10 | Implementation Plan | No work has been done for high-level implementation estimating for cost or schedule
11 | Licensing (SW) | Requires new licensing agreements - possible delay
12 | Metrics | We do not have the metric data available to validate benefit value realization
13 | PCR | Vendor has history of low-ball with high number of PCRs
14 | Project Complexity/Architecture | The project involved many new vendors, suppliers and is considered higher risk. The architecture of the proposed software is radically different from what we have.
15 | Quality | Quality standards for the project and products have not been established
16 | Regulatory Assessment Completed | Regulatory requirements not fully understood or not fully defined
17 | Reliability, Capacity and Performance | Impact on business is not fully understood or estimated
18 | Resource Availability | Resource availability is not known. Resource commitment not confirmed
19 | Resource Skills | Skills are not in-house, requires staff augment resources or consulting
20 | Safety | Ameren and contractor safety plans not developed or deployed
21 | Scope | Scope is unclear. Scope is not agreed to by all stakeholders
22 | Technology Maturity | Interdependent upon old technology/systems/applications
23 | Training | Training plan and budget not established
24 | Organizational Change Management | No Organizational Change Management is planned or budgeted
25

## 11 Guide - Success Criteria
Guidelines for Business Objectives and Project Success Criteria
This guide illustrates the distinctions between Business Objectives and Project Success Criteria for teams completing Initating phase documents including Opportunity Overviews, Business Cases and Charters.

## 12 Guide - Data Dictionary
Data Dictionary - Selected Fields
Fields are not number on the form, these are listed from top left corner to bottom right corner
Tab | # | Field Name | Description
2 | 1 | Project Name | Pulled from OO
2 | 2 | Prepared by | Last Name, First Name
2 | 3 | Date Prepared | MM/DD/YYYY
2 | 4 | Document Repository | Your "Portfolio Channel on the Demand Planning Site"
2 | 5 | Unique ID | Assigned by PMO during Opportunity Overview Phase of Demand Planning - fixed and cannot be changed
2 | 6 | BL Sponsor | Last Name, First Name
2 | 7 | BL Contact | Last Name, First Name
2 | 8 | Digital Director | Last Name, First Name
2 | 9 | Digital Contact | Last Name, First Name
2 | 10 | Digital Portfolio Lead | Last Name, First Name
2 | 11 | Digital PM | Last Name, First Name
2 | 12 | Digital and BL BPS | Last Name, First Name
2 | 13 | Hoshin Pillar | Select most appropriate Pillar based upon primary intended impact of project - at a high level, what is this project essentially about?
3 | 14 | Hoshin High Level Objective | Select most appropriate HLO that will be driven by the project - Many projects impact multiple HLOs, pick the most important HLO
3 | 15 | Rationale for Project Alignment | Enter text explaining why you selected the HLO most driven by the project outcomes. How will the project benefits drive the realization of this HLO?
3 | 16 | Expected Delivery Method | Select best method to accomplish the business objectives within the desired time-frame and realistic resource levels
3 | 17 | CPOC/SLPOC Project Number | For projects over $5M, project team will follow SLPOC Policy and Procedures, for projects over $20M, project team follows CPOC Policy and Procedure
3 | 18 | Compliance Project | If the driving force to initiate the project is compliance, then the project is prioritized based upon mandatory compliance due dates
| 19 | Asset Corp(s) | Select the legal entity that will own the assets put into service as a result of this project
| 20 | Asset Life | Select the most appropriate asset life - if 10 yr. or 15 yr. is selected, contact Plant Accounting as this would unusual and make sure you understand proper asset life.
| 21 | Asset Retirements | If your project is replacing an asset, contact Plant Accounting to secure the current Net Book Value and enter in this field…this is not automatically included in tab 3 Financials
| 22 | R&D Tax Credit | If your project involves work to "eliminate uncertainty for capabilities, methodologies or design" needed to complete your project, your costs associated with those activates may qualify for an R&D tax credit. See the Shark Tank SharePoint site, section titled "R&D Tax Credit" information go tools and guidance. Mark this field yes if you believe some of your costs qualify. Contact Debbie Schneider in Tax if further advisement is needed.
| 23 | Investment Portfolio | This is a selection of one of the investment portfolios defined in UIP - B&CS, Customer, Cybersecurity, ED, Foundational Enablers, Generation/Nuclear, Transmission, Run The Business
| 24 | Cloud Solution | This field is to assist classifying projects for analysis of driving strategy to move to a more significant cloud architecture
| 25 | Estimated Undivided Joint Interest | Enter the split of cost ownership between the primary legal entities - must total 100%
| 26 | Preferred Start Date | Enter the most realistic date known - work backward from required in-service dates, factor in resource availability if known, gate requirements, operations calendars etc.
| 27 | Estimate Duration | Best estimate known at this point
| 28 | Estimated In-service Date | Target known in-service date requirements driven by operational needs, go-live dates etc.
| 29 | Estimated Completion Date | Best estimate known at this point
| 30 | Confidence in Data/Information | Captured during OO sessions, copied here
| 31 | Primary Value Driver (by Segment) | Select best summary of the value driving the prioritization of the project - Financial, Customer, Operational, Culture
| 32 | Program Management | The business case is designed for a single project, but some projects need to have governance oversight through Program Management…if this business case represents a Program, indicate so. See the Opportunity Consolidation Guidelines and Process resource document in "Demand Planning>General>Files>2019 Business Case Resources" for guidance on using this field.
| 33 | Business Case Status | Select most appropriate status - Most Business Cases stay in Development until PAC approval. If your project was stopped for any reason, change to that status and make notes in the Team Note tab.
| 34 | Business Case Priority for Budgeting | This is used to sort all business cases for Segment meetings or other prioritization discussion in getting ready for the budgeting process.
| 35 | Work Order List | Once the Business Case is approved, work orders can be generated and once created, should be entered into this field to record work orders that have been authorized
| 36 | Background, Objectives, Strategy Alignment | This field focuses on what's driving the need for the project, establishing SMART Goals for the business objectives and the business benefits. Make you list exhaustive, but concisely described, such that anyone could read and quickly grasp the relevance of the project to the objectives
| 37 | Business Outcome Benefits | This field is to further demonstrate how achieving each objective above will result in desired performance improvement for the business and/or Digital.
| 38 | RT | RT=Resource Type - these are used by Digital BPS's to load UIP with project budget and forecast data
| 39 | WACC | Weighted Average Cost of Capital - Corporate overall figure from Treasury - updated by Treasury Quarterly, WACC should be updated for project budgeting.
| 40 | NPV | Net Present Value - Standard Excel Calculation of cash flows starting with project costs as 1st year or two cash outflows (negative), followed by 4 years of benefits, which can be positive or negative, discounted by Treasury Corporate WACC.
| 41 | Indirect Overheads | Protected field - Corporate rate
| 42 | AFUDC | Protected field - Corporate rate

## 11 Data Validation Tables (hidden)
Workbook Data Validation Tables
Do Not Alter
This tab to be hidden
| Tab 3 Project Definition |  | Tab 4 Financials |  | Context Sensitive Look Up Tables for Hoshin
| Field Name | Selection Criteria | Field Name | Selection Criteria | Fields below are part of table - intentionally blank
| Portfolio Manager | Dave Burbridge |  |  |  | Digitize | Simplify | Innovate | Culture | Governance
|  | Cort Hacker |  |  |  | Omni – Channel Customer Experience | Digital Field Experience | Advanced Analytics and Automation | Agile and User-Centric Design | Portfolio, Program and Project Management
|  | Eric Robinson |  |  |  | Smart Meters | End-to-End Process Approach | Grid of the Future | Business Alignment and Strategic Partnerships | Digital Vendor Management
| Expected Delivery Methodology | Agile |  |  |  | Seamless Coworker Experience | Operational Excellence |  | Workforce Strategy | Foundational Capabilities
|  | Iterative | [7 empty] | Cybersecurity and Regulatory Compliance
Waterfall
| Regulatory Project? | Yes
No
| Undivided Joint Interest | AMO
AIC
ITC
| Asset Corps | AMO
AIC
AMS
AMO and AIC
|  | AMO, AIC and ATX |  |  | Revision Log
AMO, AIC and ITC
|  | AMO, AIC, ATX and ITC |  |  | 2018-07-09 | Workbook Version Number | v7-9F | Named additional fields for data retrieval
ATX
ITC
| R&D Tax Credit? | Yes
No
| Investment Portfolio | B&CS - Finance
B&CS - HR
B&CS - Supply Chain
B&CS - Other
Customer
Cyber
ED
Foundational Enabler
Generation/Nuclear
Run the Business
Transmission
Other
| Cloud Solution | Yes
No
| Data Confidence Level | High - Vendor Bid/Est In-hand
Medium - Similar/Historical Project
Low - Placeholder Pending Definition
| Risk Impact | High
Medium
Low
| Digital BC Leads/Directors | Anders, Pam
Brown, Wendy
Bryant, Charles
Delanela, Ann
Gibbs, Ryan
Heger, Mary
Herr, Eric
Hughes, John
Knobbe, Jay
Moore, Chuck
Ose, John
Rajan, Sam
Schaeffer, Charlie
Shadduck, Jon
Siedband, Mark
Solari, Joe
Straughn, Paul
Wischnowski, Jen
| Compliance Sources | NERC
FERC
Regulatory
Legal
Other
| Asset Life | 5 yr
10 yr
15 yr
other
| Value Drivers for AMO and AIC | Financial
Customer
Operational
Culture
| Business Case Status | In Development
Approved
Stopped
| Priorty for Budgeting | 1- High
2 - Medium
3 - Low
| Program or Project | Program
Project