## ESO Release 3 - UAT test defect
Issue key | Status | Summary | Assignee | Issue Type
ESO-500 | Open | Correct Deposit Messaging | Katta, Swapna | Bug
ESO-505 | Open | Service type missing on the summary page in PLZ | Katta, Swapna | Bug
ESO-513 | Open | Pending Order-Click Submit Not Working | Katta, Swapna | Bug
ESO-512 | Open | Order Held and Should not be Held | Rickard, Christopher S | Bug
ESO-511 | Open | Learn More Link-No Content and Looping | Katta, Swapna | Bug
ESO-510 | Open | Guest Pay-Credit Card Redirected to Contact Us | Katta, Swapna | Bug
ESO-468 | In Progress | Windows not working in CSSPX4 Build- | Katta, Swapna | Bug
ESO-509 | Resolved | Obligation Added for Held Order is Blank | E112521 | Bug
ESO-508 | Resolved | MO Denial of Service Contact has wrong name | E112521 | Bug
ESO-461 | Resolved | Success Page-Fix Punctuation in the IL Supply Choice message | Yeluri, Madhu | Bug
ESO-459 | Resolved | Error after reviewing service type | Yeluri, Madhu | Bug
ESO-11 | Closed | New customer of records are unable to successfully connect service online | Katta, Swapna | Bug
ESO-491 | Closed | Bankruptcy Accounts displaying in the List to pay on Web | E44742 | Bug
ESO-457 | Closed | Order Not Held-No Obligation Created & No Critical Contact | E112521 | Bug
ESO-456 | Closed | Connect Pending Screen Missing Address etc. | E112521 | Bug
ESO-458 | Closed | Deposit not assessed | Rickard, Christopher S | Bug
ESO-445 | Closed | Unable to access Start stop Move in Web URL | E44742 | Bug
ESO-460 | Closed | Western Union Credit Card payment link | E23945 | Bug
ESO-495 | Closed | ESO 59 Success Page - "Error" message shows | Q154914 | Bug
ESO-471 | Closed | CSS Environment Repair Static Tables | Q151198 | Bug
ESO-474 | Closed | AMI Disconnect did not function with correct Order Date Availability | Q151198 | Bug
ESO-469 | Closed | Same Error on Disconnect in CSSPX4 | E44742 | Bug
ESO-416 | Closed | Connect-Written off account not in held status | Rickard, Christopher S | Bug
ESO-421 | Closed | Connect-Obligation fields are empty | Rickard, Christopher S | Bug
ESO-422 | Closed | Connect-WORF Guest Pay page | Katta, Swapna | Bug
ESO-411 | Closed | Account Dashboard-Connect for bankruptcy customer-message missing | E112521 | Bug
ESO-410 | Closed | MO Connect Success Page | E112521 | Bug