## Implementation Checklist
12/18/18 Implementation Checklist
Task | Task Description | Team | Assigned | Start Date | Est Start Time | Finish Date | Est Finish Time | Status | Comments
101 | UAT Testing | ESOT | Dorge, Katherine L Mercado, Claudia | 11/2/`8 | NA | 2018-12-07 | NA | 100% pass
102 | Deployment - Go/No Go call/approval | ESOT | Humphrey, Amanda S | 2010-12-10 | NA | 2018-12-10 | NA | Approved
103 | Code Push - Go/No Go decision for Release based on whether conditions | ESOT | IT/Release Management | 2018-12-17 | 12noob | 2018-12-17 | 5pm
104 | Code Push to production | ESOT | Rickard, Christopher S; | 2018-12-18 | 3am | 2018-12-18 | 3:30am
105 | Regression Testing | ESOT | Dorge, Katherine L Mercado, Claudia | 2018-12-18 | 3am | 2018-12-18 | 4am
106 | Go/No Go call/approval | ESOT | Humphrey, Amanda S | 2018-12-18 | 3am | 2018-12-18 | 4am
107 | Code Back out - If necessary | ESOT | Rickard, Christopher S; | 2018-12-18 | 4am | 2018-12-18 | 4am |  | New Code deployed can be Backed out. Back out plan is implemented if regression test fails.
108
109
110

## Contacts
Name | Team | Support Level | Work | Home | Cell
Dorge, Katherine L | ESO | Sr, Business Analyst
Humphrey, Amanda S | ESO | Product Owner
Mercado, Claudia | ESO | Sr, Business Analyst
Rickard, Christopher S; | ESO | Development Lead
McCleary, Darnette M | PMO | Project Management
Jenkins, Jeronica A | Digital Customer Products | Portfolio Management

## Backout Plan
Backout Plan
Seq | Task Description | Dependency | Team | Assigned | Est. Time | Status | Comments
100 | Implementation - Rollback Plan
101
102 | Code will be able to pull back and restore the original code | Regression Testing | ESO | Rickard, Christopher S | 15 minutes
103
104
105
106
107
108
109
110