## Slide 1
To Do
Work that has not been started
In Progress
Work that is actively being looked at by the team.
Code Review
Work that is completed, but awaiting review.
Done
Work that is completely finished and meets the team's definition of done.

## Slide 2
JIRA terminologies
Issue:
In Jira Software, issues typically represent things like big features, user requirements, and software bugs.
Sub-Task: You might create sub-tasks for any of the following reasons:
To split an issue into even smaller chunks
To allow various aspects of an issue to be assigned to different people
To create a to-do list for an issue
(To create a sub-task: 1- Navigate to an issue, and select more ( ••• ) > Create Sub-Task.
2-Fill in the details as needed, and then click Create.)
Estimate –in Story points: To set an estimate for an issue:
1-In your Scrum project, select an issue either on your board, or in the backlog.
2-In the issue details, click the Estimate field.
3-Enter an estimation
Rank an Issue: In a Scrum project, when planning your next sprint you might rank the issues in your backlog, and then decide to put the first 10 (or however many issues the team is capable of completing) into the sprint.
Filter an Issue:

## Slide 3
Filter issues
An issue filter allows you to hide the issues you don't want to see, and zone in on the ones you want to focus on. Jira Software has Quick filters, which allow you to filter the issues on your board. Here's what they look like on Scrum/Kanban boards:
Search bar: Display issues that contain a search term, and hide the rest.
Quick filters menu: By default, you can filter by issues assigned to you, and issues recently updated. Any Quick filters you create will also display here.
Assignee menu: Only display issues assigned to people you select.
To create your own Quick filters (Scrum and Kanban boards):
Go to your board, then select more ( ) > Board settings.
Click the Quick Filters tab.
Enter a name, JQL query, and description for the filter. For more information on JQL, check out our advanced searching documentation.
Click Add.
Flagging an issue: is useful because it encourages collaboration and communication throughout the team.
Here are some examples:
You're working on a task, but realize you don't have capacity to finish it off. You can flag the issue, and a team member with spare capacity who looks at the board can jump on and help.
An issue you're working on becomes blocked. You can flag the issue, add a comment explaining the blocker, and move on to the next task. Anyone who looks at the board will see that it has been flagged, and understand what's going on when they open it.

## Slide 4
Agile project management style: which takes an iterative approach to development with regular feedback intervals. These iterations allow for the team to be diverted to (and productive in) another area of the project while a blocking issue is resolved.

## Slide 5
How to build a great agile program:
When a program transitions from traditional project management to agile, the team and the stakeholders must embrace two important concepts:
The product owner's focus is to optimize the value of the development team's output. The development team relies on the product owner prioritizing the most important work first.
The development team can only accept work as it has capacity for it. The product owner doesn't push work to the team or commit them to arbitrary deadlines. The development team pulls work from the program's backlog as it can accept new work.
Let's explore the mechanisms agile programs use to organize, run, and structure work in an iterative way.
Roadmaps:
A roadmap outlines how a product or solution develops over time. Roadmaps are composed of initiatives, which are large areas of functionality, and include timelines that communicate when a feature will be available. As the program develops, it's accepted that the roadmap will change–sometimes subtly, sometimes broadly. The goal is to keep the roadmap focused on current market conditions and long-term goals.
Requirements
Each initiative in the roadmap breaks down into a set of requirements. Agile requirements are lightweight descriptions of required functionality, rather than the 100-page documents associated with traditional projects. They evolve over time and capitalize on the team's shared understanding of the customer and the desired product. Agile requirements remain lean while everyone on the team develops a shared understanding via ongoing conversation and collaboration. Only when implementation is about to begin are they are fleshed out with full details.
Backlog
The backlog sets the priorities for the agile program. The team includes all work items in the backlog: new features, bugs, enhancements, technical or architectural tasks, etc. The product owner prioritizes the work on the backlog for the engineering team. The development team then uses the prioritized backlog as its single source of truth for what work needs to be done.
Agile delivery vehicles
Agile can be implemented using various frameworks (like scrum and kanban) to deliver software. Scrum teams use sprints to guide development, and kanban teams often work without fixed work intervals. Both frameworks, however, use large delivery vehicles like epics and versions to structure development for a synchronized release cadence out to production.
Agile metrics
Agile teams thrive on metrics. Work in progress (WIP) limits keep the team, and the business, focused on delivering the highest priority work. Graphs like burndown and control charts help the team predict their delivery cadence, and continuous flow diagrams help identify bottlenecks. These metrics and artifacts keep everyone focused on the big goals and boost confidence in the team's ability to deliver future work.
Agile runs on trust
An agile program cannot function without a high level of trust amongst team members. It requires candor to have difficult conversations regarding what's right for the program and the product. Because conversations happen at regular intervals, ideas and concerns are regularly expressed. That means team members also have to be confident in each other's ability (and willingness) to execute on the decisions made during those conversations.
In summary, agile development is a structured and iterative approach to making software. It gives you the ability to respond to change without going off the rails. And that's good news for any program.

## Slide 8
What are stories, epics, initiatives, and themes?
Stories, also called “user stories,” are short requirements or requests written from the perspective of an end user.
Epics are large bodies of work that can be broken down into a number of smaller tasks (called stories).
Initiatives are collections of epics that drive toward a common goal.
Themes are large focus areas that span the organization.