- Managing Blended Initiatives

Contents

Overview	2

Work Type, WBS Combinations	3

Waterfall - Agile Intersection Points	4

Project Management in a Blended Initiative	5

To Split or Not to Split	5

Project Planning	6

Artifact Management	7

Financial Management	7

Artifact/Process Table	8

# Overview

The purpose of this document is to raise awareness and provide guidance on interface points between Agile Teams and Waterfall Teams working on blended initiatives.  An initiative is the scope of work defined in the IT Work Request. A blended initiative is a single initiative using multiple development methodologies (e.g., Agile, Waterfall, etc.).

Within these blended initiatives, multiple interaction points between the Agile and Waterfall teams occur throughout the lifecycle of the project. It is critical for the Lead PM to ensure communication and coordination among all impacted stakeholders (delivery teams, release managers, solution architecture, testing, etc.) so that a successful product can be delivered.

The following sections will help document blended project scenarios, introduce the Waterfall-Agile Intersection Points and provide an overview of Project Management best practices when managing within a blended environment. Finally, a detailed walkthrough of the software lifecycle is provided along with guidance for Agile and Waterfall teams to consider when working on blended initiatives.

.

# Work Type, WBS Combinations

Within the PRISM Project Workflow Module, Work Type indicates the kind of work being performed. The selected Work Type helps determine which Work Breakdown Structure is applicable. For additional guidance, refer to the IT UP Topic, “Setting Up the Workflow Template View”.

The information below is extracted from “Setting Up the Workflow Template View” Topic and is provided for reference purposes.

| Initiative Type | Work Type | WBS |
| --- | --- | --- |
| All application teams are Waterfall | IT Unified Process Project | Standard |
| All application teams are Agile | IT UP Agile | Agile |
| Scenario 1 – Not Blended Decision to split Different components of the solution can be delivered separately, and be ready for their intended use once delivered to the client. | Waterfall PID: IT Unified Process Project Agile PID: IT UP Agile | Standard Agile |
| Scenario 2 - Blended Decision to split Multiple components of any part of the solution must be delivered together in order for that part to be ready for its intended use once delivered to the client. | Waterfall PID: IT UP Agile Blended Agile PID: IT UP Agile Blended | Standard Agile |
| Scenario 3 - Blended Decision not to split Multiple components of any part of the solution must be delivered together in order for that part to be ready for its intended use once delivered to the client. | IT UP Agile Blended | Standard |

# Waterfall - Agile Intersection Points

The following chart aligns IT UP Waterfall Milestones and Artifact/Packages to IT UP Agile Core Processes. The intent of the chart is to depict the intersection touch points of the two Software Development Life Cycles. For each intersection touch point, guidance on how the project teams can interface is provided later in this document.

# Project Management in a Blended Initiative

Upon a review of the “Waterfall - Agile Intersection Points” table in the previous section, it is evident that there are various interface points within a blended initiative that will require special attention by an IT Project Manager.  This section will provide some guidance regarding the treatment of these interface points.

## To Split or Not to Split

A blended initiative will require the project team to determine if the effort will be managed under a single PRISM PID or under multiple PIDs by SDLC.  Project splits are to be managed within guidelines published by IT Governance and Cost Management, IT UP, etc., noting that each PID will be evaluated independently to determine software capitalization. Listed below are considerations to be taken into account when determining to split or not to split.

Level of Effort:  The level of effort associated with the Waterfall and Agile SDLC’s may help determine if a split is necessary.  Minimal impacts to either the Waterfall or Agile application(s) may make the overhead associated with managing the split cost ineffective.  Likewise, significant impacts to either Waterfall or Agile application(s) may support the decision to split the effort.

Documentation and Milestone Impacts: For blended initiatives falling within Initiative Type Scenario 3 in the preceding table and using the Standard WBS, milestones M5 through M8 will remain open for projects involving Agile applications.  If the Waterfall team(s) cannot support this, the project should be split.  The Waterfall team can create and baseline their own IT UP packages while the Agile team does not finalize and baseline their packages until the last iteration.  Another factor that may impact the decision to split is the ability of the split project to inherit or create artifacts at a project or initiative level.

Software Capitalization Impacts:  If an initiative involves software capitalizable work, the Project Manager will need to be aware that this could factor into the decision to split.  If the project split does not deliver significant new functionality, then it would not qualify as software capitalizable.  Therefore, the split would create an expense-only project and splitting may not be advisable due to potential budgetary concerns. For additional guidance, refer to the topic, “Maximizing Software Capitalization and Minimizing Splits”.

## Project Planning

In a blended initiative, it is imperative that the Project Plan document details how the initiative will be managed and coordinated between the two SDLC methodologies.  Some of the items that should be considered during the planning for an initiative are identified below.

- When managing in a blended environment, it is recommended that all related PRISM PIDs share a common project plan to ensure a single point of access for critical information.

- The project plan should describe locations for all information related to the project and communication plans for keeping all teams in synch.

- The project team should determine and document in the project plan what tools will be used to manage Requirements/User Stories per the IT UP PRISM & SDLC Tools/Tool Inventory/Mandated Tools for Requirements.

- The project team must also explain in their project plan how they are going to ensure traceability exists for the initiative.  Traceability must exist from scope (what’s funded) to what is ultimately delivered for the entire initiative, especially in situations where multiple tools are used to track requirements and User Stories.

- The coordination of schedules between the Agile and Waterfall teams will be critical in the project planning for the initiative, especially with regard to Release Planning, Testing, Change Management and project communications.

- The Social Agreement/Project Plan should detail communication between the Agile and Waterfall teams for status, defects, testing, issues and any other pertinent communications.

- It is imperative that the dependencies among and between projects, sub-projects and applications are clearly understood. While operating at the project level is manageable in an environment when subprojects or applications are not dependent on other sub-projects or applications, those that are dependent upon others should be thoroughly documented and tracked in the project plan. The dependencies would be identified as part of the initial release planning meeting, and tracked and updated in the release plan/timeline.

- Since Test strategy is a part of the project plan, specific test dependencies, coordination of defects, test tools used by team and agreed upon exit criteria should be identified. This could also be tracked in the timeline/Release Plan.

- For Risk Management, refer to IT UP Topic Managing Risk, Issues, Action Items and Jeopardies.

## Artifact Management

The artifacts required for an initiative should be managed in accordance with IT UP and are expected to meet process guidelines.  Below are some considerations associated with managing these artifacts.

- The project team should identify which artifacts, if any, will be inherited by the split project. For additional guidance, refer to the IT UP Topic, “Requesting and Managing Project Splits”.

- Blended initiatives falling within Initiative Type Scenario 3 must follow the guidelines for managing the Standard WBS in PRISM.  See table for additional guidelines and recommendations on how to satisfy the content requirements in ITUP.

- For blended initiatives falling within Initiative Type Scenario 3 in the preceding table and using the Standard WBS, project milestones M5 through M8 will remain open until all iterations are complete. These milestones will need to be closed prior to closing M9.

- For blended initiatives falling within Initiative Type Scenario 3 in the preceding table and using the Standard WBS, packages within M5 through M7 milestones should reflect a completion date corresponding to the date the package was baselined.

## Financial Management

Project Managers managing a blended initiative should demonstrate prudent financial management.  Some financial considerations are referenced below.

- Agile project budget reviews should be completed following each iteration prior to the start of the next iteration.

- TCP estimates should be completed as agreed upon for each impacted project.

# Artifact/Process Table

Use the table below to understand the various touch points and considerations when operating in Scenario 2 or 3 from the previous Work Type, WBS Combinations table.

For Scenario 1 – Not Blended, Waterfall Team will follow IT UP Standard WBS and Agile Team will follow IT UP Agile WBS as defined by IT Unified Process.

| Waterfall Artifacts | Agile Artifacts/ Processes | Considerations & Guidelines | Blended Split Scenario 2 | Blended No Split Scenario 3 |
| --- | --- | --- | --- | --- |
| Phase 1 Package Project Readiness Package Solution Definition for Estimation | Solution Definition for Estimation | In this stage of the SDLC, the Client work initiative is received by the Project Team(s) and steps are initiated to obtain a clear and common understanding of the work initiative. The Waterfall Team and the Agile Team will need to work together to identify the scope that they will be responsible for. To reach a common understanding, having the Waterfall Team attend the Agile Team’s Vision Meeting will be crucial and each team will begin to provide input for the creation of a single Solution Definition document. Based on “To Split or Not to Split” section above, a decision will be made as to whether to move forward as a single PRISM Project (PID) with two SDLC Teams or split the scope into two PRISM Projects (PIDs); with one PID adhering to the Waterfall SDLC and the other PID adhering to the Agile SDLC. Both Teams will be creating estimates by the end of this activity. |  |  |
| Solution Definition for Project Architecture | Solution Definition for Project Architecture | Each team engaged in the initiative will need to work together along with the Solution Architect to consolidate information for the Solution Definition. One Solution Definition document should be created for the initiative and shared by all teams and made accessible to all PRISM PIDS supporting the initiative. The Solution Architect validates the document applies to both teams (Both PIDs). Teams must ensure all business requirements/User Stories impacting the solution are captured, stable and reviewed for quality prior to the creation of the Solution Definition for Project Architecture. |  |  |
| Target Release | Release Planning and Management Process | There needs to be a shared release plan for components that must come together in order for the solution to be ready for its intended use, but are being delivered by different teams. The overall goal is to understand deployment dependencies and communicate, as appropriate, between the teams and with Release Management. There are several options for this, but the release plan should be documented in the project plan and agreed to by all impacted parties. Recommended Options: - Hold joint release planning meetings and develop a shared release plan - Release Targeting, as documented in IT UP for both Waterfall and Agile should be initiated in parallel by the PM as an output of the joint Release Planning meeting prior to the first Iteration. - Identify representatives from each team to participate in release planning meetings across teams - Ensure open communication between teams on initial and ongoing Release Planning, including the Target, Commit and/or any changes to the Release. | For the project assigned to the Standard WBS set the target release date in WBS communicating target release planning is completed. For the Agile WBS there is no additional PRISM updates needed for this activity. | For Standard WBS set the target release date in WBS communicating target release planning is complete for the initiative. |
| Business Requirements Package System Requirements Package | User Stories | The Agile Team and the Waterfall Team must be aware and understand what requirements are being delivered by the other team, including how the work is divided. The plan for remaining in synch should be documented in the project plan. Recommended Communication Vehicles - Agile Team(s) participate in Waterfall Team(s) formal review of Artifacts - Waterfall Team(s) attend Vision Meeting, Backlog Grooming and Iteration Planning Meetings for those sessions where the Waterfall Team is impacted - All teams should be represented in Scrum of Scrum meetings User Story/Requirements Management In a blended environment, where components must come together in order for the solution to be ready for its intended use, but are being delivered by different teams, it is necessary to ensure the whole set of “requirements (whether represented by BRs/SRs or User Stories created according to the IT UP topic, User Story Management Standards) are available for downstream stakeholders (e.g., Integrated System Test, etc.). Teams must ensure these requirements impacting the solution are captured, stable and reviewed for quality prior to the creation of the Solution Definition for Project Architecture. The teams need to devise a joint strategy to share this information in a common way. This strategy should be documented in the project plan. Recommended Options: - Option 1: Load all Requirements in ReqPro if a holistic view is required, i.e. Agile User Stories need to be loaded into ReqPro - Option2: Leave Agile User Stories in an approved TSS Standard Tool. Download or export as needed to provide the information to the Waterfall Team. Waterfall Team downloads or exports Waterfall requirements from ReqPro to provide information to the Agile Team - Option 3: Create a xls containing Requirements from ReqPro and User Stories from an approved TSS Standard Tool | For the project assigned to the Standard WBS complete the BR/SR as per the process. For the Agile WBS there is no additional PRISM updates needed for this activity. | The Agile Team(s) must do one of the following: - Add a statement to the Waterfall Team(s) Business Requirements and System Requirements that provides the location of the User Story repository. - Create a separate Business Requirements and System Requirements and adhere to the IT UP Standard WBS Artifact/Package Requirements. - Ensure the Project Plan has a link to the User Story repository and link the Project Plan to the Artifact in the WBS for both the Business Requirements Package and System Requirements Package. Enter Comments for both Packages, “See Project Plan for Agile User Story Repository”. |
| SR Architecture Assurance Screen Results | SR Architecture Assurance Screen Results | Because components must come together in order for the solution to be ready for its intended use, Assurance Architects need to understand the whole solution to be able to provide the assessment. Additional information relating to what Architecture Assurance screens are required can be found in the Architectural Assurance Guidelines. The teams need to devise a joint strategy to share this information in a common way, working with the Assurance Architect. This strategy should be documented in the project plan. | For Standard WBS set the AASR Actual End Date in WBS communicating when the AASR was completed. For the Agile WBS there is no additional PRISM updates needed for this activity. | Set the AASR Actual End Date in WBS communicating when the AASR was completed. |
| Phase 3 Readiness Package | Iteration Zero Complete | Though budgets on each PRISM Project PID will be managed independently, they most likely will be approved by the same SI Owner. Communication of approved budgets should be shared between the two SDLC Teams. At this point within the SDLC, an opportunity to revise the budget, if needed, exists since the teams will have more information regarding the CAP/Expense Spread. Teams are expected to stay within that budget regardless of how many times the project may split. The estimates/budgets are expected to reflect the current and known best view at all times. Note: The TCP2 Budget is required if the SI supporting the effort requires a Funding Authorization. | For Standard WBS set the Actual End Date in WBS for Phase 3 Readiness Package artifact. For the Agile WBS set the Actual End Date in the WBS for Iteration Zero Complete. | Set the Actual End Date in WBS for Phase 3 Readiness Package artifact when the Phase 3 Readiness Package activities and the Iteration Zero activities have been completed. |
| DG2 Package | Project Plan | Because of the high level of coordination required in scenarios 2 and 3 in the preceding table, it is recommended that a single shared project plan be developed and maintained. The teams need to communicate and collaborate on developing the Project Plan(s) to ensure proper planning. | For Blended Initiatives using both the Standard and Agile WBS it is recommended that a single shared Project Plan be developed and maintained and linked to the appropriate artifact(s) in WFT. | For Blended Initiatives using the Standard WBS, the project must adhere to the IT UP Standard WBS DG2 Artifact/Package Requirements, which will include the creation of a single shared (Waterfall and Agile Team) Project Plan. |
| Business Case Approval Evidence | Business Case Approval Evidence | Business Case Approval evidence is provided for all projects within an Strategic Initiative. See the activity “Validate Funding Authorization” under Global processes Strategic Initiatives for more information on submitting and obtaining approvals for funding. A separate Business Case is not needed for each additional project being funded under the SI. The Lead PM should reach out to the SI owner to verify if the SI requires a Business Case and if yes, do they have approval to spend. This would only need to be done once for the funded initiative and shared and linked to both PRISM WBSs. | Approval is handled the same in both Standard and Agile WBS. | Approval is handled the same in both Standard and Agile WBS. |
| HLD Package | Iteration and Deployment Management Process | Because components must come together in order for the solution to be ready for its intended use, it is recommended that a shared HLD is developed that clearly defines which components will be delivered by each team to avoid potential conflicts and rework. This also assists roles responsible for downstream deliverables to understand which team will be delivering which components. | For Blended Initiatives using both the Standard and Agile WBS, follow appropriate WBS guidelines. | For Blended Initiatives using the Standard WBS, if an HLD is required, the Agile Team(s) may follow one of the listed options: - Add a statement to the Waterfall Team(s) High Level Design that provides the location of the User Story repository. - Create a separate High Level Design and adhere to the IT UP Standard WBS Artifact/Package Requirements. - Ensure the Project Plan has a link to the User Story repository and link the Project Plan to the Artifact in the WBS for High Level Design Package. Enter Comments, “See Project Plan for Agile User Story Repository”. |
| AID Package | Iteration and Deployment/ Execute Iteration / AID |  | For Blended Initiatives following this scenario, follow the appropriate WBS Requirements. | For Blended Initiatives using the Standard WBS, follow the standard WBS Artifact/Package Requirements. |
| HLD/AID AA Screen Results | HLD/AID AA Screen Results | Because components must come together in order for the solution to be ready for its intended use, Assurance Architects need to understand the whole solution to be able to provide the assessment. Additional information relating to what Architecture Assurance screens are required can be found in the Architectural Assurance Guidelines. The teams need to devise a joint strategy to share this information in a common way, working with the Assurance Architect. This strategy should be documented in the project plan. | For Standard WBS set the HLD/AID AASR Actual End Date in WBS communicating when the HLD/AID AASR was completed. For the Agile WBS there is no additional PRISM updates needed for this activity. | Set the HLD/AID AASR Actual End Date in WBS communicating when the AASR was completed. |
| Release Commit Request | Release Commit Request | Each team commits to a Release following IT UP. Ensure open communication between teams on Release Planning, including Commit and/or any changes to the Release. Release Commitment should be initiated by the PM as documented in IT UP for both Waterfall and Agile components in parallel, at the critical intersection point shown when the Waterfall teams are at M5 and the Agile teams are again doing Release Planning/Mgmt. For Scenario 3, Release Commitment should be sought at this point even if the M5 milestone is to be kept open. The Waterfall Team needs to send a representative to the Scrum Team Release Planning meetings and vice versa. Both teams should identify a resource to act as a liaison. The Waterfall Team Release Planning meetings and the Scrum Team Release Planning meetings can be held jointly. The overall goal is to understand deployment dependencies and communicate, as appropriate, between the teams and with Release Management. | For Blended Initiatives following this scenario, follow the appropriate WBS Requirements. | For Blended Initiatives using the Standard WBS, follow the standard WBS Artifact/Package Requirements. |
| Design Package | Agile Tool | The teams need to review the other team’s design work and attend review sessions. If it is determined that the Application Design information needs to be shared between the Waterfall team(s) and the Agile team(s), then ensure necessary communication and coordination takes place. | For Blended Initiatives using both the Standard and Agile WBS, follow appropriate WBS guidelines. | or Blended Initiatives using the Standard WBS, the Agile Team(s) may either: - Add a statement to the Waterfall Team(s) Design Package that provides the location of the User Story repository. - Create a separate Design Package and adhere to the IT UP Standard WBS Artifact/Package Requirements. - Ensure the Project Plan has a link to the User Story repository and link the Project Plan to the Artifact in the WBS for Design Package. Enter Comments, “See Project Plan for Agile User Story Repository”. |
| TCP3 | Monitor and Control Budget | If the PIDs are split (Scenario 2 above), the Waterfall Team will produce a TCP3 estimate and budget while the Agile Team will perform budget checks with each iteration. If working in a single PID (scenario 3 above), in order to support the TCP3 Budget, all Waterfall teams are required to produce a TCP3 estimate. It is the LPM discretion to determine if Agile teams will need to produce a TCP3 estimate or use the existing validated estimates for the Agile certified applications. | For Standard WBS set the Actual End Date in WBS for the TCP3 estimate artifact. For the Agile WBS, there are no updates required in PRISM/WBS. | Set the Actual End Date in WBS for the TCP3 estimate artifact when the estimate is completed and/or validated for all teams. |
| Development Package | NA |  | For Blended Initiatives using both the Standard and Agile WBS, follow appropriate WBS guidelines. | For Blended Initiatives using the Standard WBS (Scenario 3), the Agile Team(s) may follow one of the listed options: - Create a separate Development Package and adhere to the IT UP Standard WBS Artifact/Package Requirements. - Ensure the Project Plan has a link to the User Story repository and link the Project Plan to the Artifact in the WBS for Development Package. Enter Comments, “See Project Plan for Agile User Story Repository”. |
| Test Package Test Package Template (All test cases must trace to requirements) | Iteration and Deployment Management Process | Shared functionality delivered by each team needs to be communicated to all delivery teams to support test case development and execution. Since information from each team’s test case development, execution and defect management is critical to the success of the other team, it is recommended to deliver a shared test plan using a single shared Test Package Template. Things to consider: - timeline - exit criteria - environment - test data - test case mgmt - traceability - defect mgmt - change mgmt. Guidance for different types of testing: - Unit/Assembly – can be independent - Functional – can be independent - IST – Need to be in a common environment. Options to consider: - Load all test cases in ALM QC if a holistic view is required, i.e., Agile test cases need to be loaded into ALM QC - Download or export from the Agile Tool as needed to provide the information to the Waterfall Team. The Waterfall Team downloads or exports Waterfall test cases from ALM QC to provide information to Agile Team - Create a xls containing test cases from ALM QC and the Agile Tool | For Standard WBS follow the Artifact/Package requirements for the Standard WBS. For the Agile WBS, document your test plan in the Project Plan or link or reference the test plan document and location in the project plan. | Follow the Artifact/Package Requirements for Standard WBS. |
| UAT Readiness | Iteration and Deployment Management Process | Teams need to agree that the initiative is ready for User Acceptance testing to begin. The agreement should be documented in the Project Plan. | For Standard WBS follow the Artifact/Package requirements for the Standard WBS. For the Agile WBS, there are no updates required in PRISM/WBS. | Follow the Artifact/Package Requirements for Standard WBS. |
| Deployment Readiness Package | Application Deployment | If any of the items in the Deployment Readiness Package cannot be done independently, then a single shared Deployment Readiness Package should be created. | For Standard WBS follow the Artifact/Package requirements for the Standard WBS. For the Agile WBS, store the Deployment Readiness Package in the Artifact View. | Follow the Artifact/Package Requirements for Standard WBS. |
| DG3 Package | Iterative Deployment Artifact/Agile SDG Template | When delivering shared components as part of the same deployment, there must be an agreement by all teams impacted that the project(s) supporting the initiative are ready to deploy. If single template is used, all projects deploying code for the initiative must be clearly documented and all controls (IST, UAT, PRC and DGnG) supporting each PID must be clearly satisfied following the appropriate IT UP methodology. Areas to consider: - Identify User Stories that support changes to production. - Defect Disposition - DGnG approvals | For Blended Initiatives following this scenario, follow the appropriate WBS Requirements | For Blended Initiatives using the Standard WBS, follow the standard WBS Artifact/Package Requirements. |
| Application Deployment | Application Deployment | As this work is performed independently, teams need to ensure dates are aligned. | For Blended Initiatives following this scenario, follow the appropriate WBS Requirements. | For Blended Initiatives using the Standard WBS, follow the standard WBS Artifact/Package Requirements. |
| Usable Asset in Production | Final Deployment | Worked independently by the Waterfall and Agile teams. | For Blended Initiatives following this scenario, follow the appropriate WBS Requirements. | For Blended Initiatives using the Standard WBS, follow the standard WBS Artifact/Package Requirements. |
| Project Closeout Package | Closure | Worked independently by the Waterfall and Agile teams. | For Blended Initiatives following this scenario, follow the appropriate WBS Requirements. | For Blended Initiatives using the Standard WBS, follow the standard WBS Artifact/Package Requirements. |
| Lessons Learned | Iteration and Deployment Management Process | The final Lessons Learned/Retrospective activities should be performed together by the Waterfall and Agile teams. | For Standard WBS follow the Artifact/Package requirements for the Standard WBS. For the Agile WBS, there are no updates required in PRISM/WBS. | Follow the Artifact/Package Requirements for Standard WBS. |
| Managing Change in the IT Unified Process | Managing Change in the IT Unified Process | Refer to the IT UP topic: Managing Change in IT Unified Process. |  |  |