## Slide 1
PROJECT STATUS FORM JOB AID

## Slide 2: PROJECT STATUS FORM – JOB AID
The Project Status Form is an important way to keep the leadership up to date with the overall status of a project. This will allow you to stay in close communication with management and exchange information about the current status of a project, including the progress against agreed upon Milestones, Cost , and Plans for the upcoming week. Link to Form
Fields | Guidelines | Examples / Options to select
Short Status Description | Update field by providing short current status of the project Rules to follow while updating the field : Begin status with status report date as "mm/ dd” Professionally written, clear and concise, free of grammatical errors. Avoid Long narratives. This section of the report should measure team productivity, comparing actual progress made over the past week to what was estimated in the previous status report. Teams should be praised for notable achievements, and attention should be called to incomplete items. Do not include Reason for Red/Yellow in Short Current Status | 07/14 – Created high level Project Plan and drafted estimates for cost and schedule. Up Next – PAC presentation on 2/2/2018 and secure approval
Weekly Accomplishments | Update field by entering at least 3 weekly accomplishments | Received sign off on Business Case Completed Preliminary scope analysis Established Project Communication
Next Significant Activities | Free Text: Update field by entering no more than 3 key activities planned for next week. | Complete Project Plan Receive approval for Project Plan Receive approval for Preliminary Estimates
IT Project Status Form > Project Status

## Slide 3: PROJECT STATUS FORM – JOB AID
IT Project Status Form > Project Status
Fields | Guidelines | Examples / Options to select
PM Assessment | Drop Down: Select the appropriate assessment indicator. -PM assessment indicator is based on PM’s confidence to mark Project as green, yellow or red based on the Project performance for the particular period. However before providing the weekly status update, the PM is required to refer to the Executive Dashboard Live Report to check if Project has Schedule , Budget , Quality status as Yellow or Red. -In scenarios where any of the schedule, cost, quality status are either red or yellow, and the PM assessment is updated as green, this status is accepted only if the PM has a Reason for Yellow or Red, a Return to Green plan, and an estimated resolution date for the ongoing issues. | Green Amber 1 = Status Improving Amber 2 = Status remains the same Amber 3 = Status deteriorating Red 1 = Status Improving Red 2 = Status remains the same Red 3 = Status deteriorating
Reason Red or Yellow | Free Text: If the Project has any of the performance indicators (Schedule, Budget, Quality, Overall PM Assessment of the Project) as Yellow or Red, then this field must be updated Rules to follow while updating the field: Specify performance indicator that is being impacted Specify the phase, related deliverables, activities that are impacted Specify reasons for why project turned yellow or red | Overall Status is yellow due to change in software & insufficient resources impacting cost & schedule at Planning Phase
Recovery Plan | Free Text: If the Project has any of the performance indicators (Schedule, Budget, Quality, Overall PM Assessment of the Project) as Yellow or Red, then this field must be updated. Rules to follow while updating the field: Outline “return to green plan” with action plans to mitigate/resolve the issue/risk, provide date for resolution. Mention the Resources/Team involved in the action plan. | On Cost impact, exploring options to reduce expenses and on schedule plan is to look at options to hire subcontractors.

## Slide 4: PROJECT STATUS FORM – JOB AID
IT Project Status Form > Project Status
Fields | Guidelines | Examples/ Options to select
Resolution Date | Update field by selecting the estimated resolution date by when the Status will return to Green (from Yellow or Red). Rules: If a Resolution date is unknown, PM to provide best estimated date and also the date cannot be in past | 2/2/2018
IT Leadership attention required (NEW) | If Project has ongoing issue/risk that is impacting the Project performance, PM to consult the issue/risk with Portfolio Leads first, and upon consultation, if Leadership Team is required to intervene for mitigating the risk/issue, then this column will be flagged as “Yes” by the Portfolio Lead. Once the issue/risk is resolved then the flag will be turned to “No” by Portfolio Lead. | Yes
 | If Project has ongoing issue/risk that is impacting the Project performance, PM to consult the issue/risk with Portfolio Leads first, and upon consultation, if the portfolio team is confident by PM’s assessment to mitigate the issue/risk without involving Leadership, then no need to flag this column as Yes, instead this will remain as “No” | No
Action requested for leadership | If "IT Leadership Attention Required" flag is turned as "Yes", PM to consult with Portfolio Team and request Portfolio Team to update this section to specify action requested for Leadership | Example 1: Seeking help to intervene and fast track ARB Approval Example 2: Seeking support in escalating schedule impact due to vendors.

## Slide 5: PROJECT STATUS FORM – JOB AID
IT Project Status Form > Project Info
Fields | Guidelines | Examples/ Options to select
Shark Tank Gate | Once Project Request is received from IT/Business and if determined to undergo Shark Tank Gate Approval Process, then use Project to select last approved gate from drop down options. If the Project is exempted from the Shark Tank Gate Approval exercise, then select as “N/A - Not Applicable.” For more information refer to Link | Gate A - Shark Tank A Gate B - Shark Tank B Gate C - Shark Tank C N/A - Not Applicable
CPOC Gate | If the Project is categorized as CPOC, Select last approved gate from drop down options. If the Project is exempted from the CPOC Gate Approval exercise then select as “N/A - Not Applicable” | CPOC G1 CPOC G1 B CPOC G2 CPOC G3 CPOC G4 N/A - Not Applicable
SLPOC Gate | If the Project is categorized as SLPOC, Select last approved gate from drop down options. If the Project is exempted from the SLPOC Gate Approval exercise, then select as “N/A - Not Applicable” | SLPOC 2 SLPOC 4 N/A - Not Applicable
QC Gate | Based on Tailoring Guidelines, select last approved gate from drop down options. If the Project is exempted from the QC Gate Approval exercise, then select as “N/A - Not Applicable” | Gate 0 - Planning Gate 1 - Requirements Gate 2 - Design Gate 3 - Build/Test Gate 4 - Implement Gate 5 - Closure N/A - Not Applicable
Go-Live Readiness | Based on Tailoring Guidelines, Select last approved gate from drop down options | Checkpoint 1 – 1 Month before Go-Live Date Checkpoint 2 – 2 weeks before Go-Live Date

## Slide 6: PROJECT STATUS FORM – JOB AID
IT Project Status Form > Project Info
Fields | Guidelines | Examples/ Options to select
Project Charter | Once Project Request is received from IT/Business and if this deliverable is a required based on tailoring guidelines then PM to provide latest status of this deliverable by selecting the drop down. If the Project is exempted for creating this deliverable, then select as “Not applicable.” | In Progress Awaiting Sign Off Completed Not Applicable
Business Case | Once Project Request is received from IT/Business and if this deliverable is a required based on tailoring guidelines then PM to provide latest status of this deliverable by selecting the drop down. If the Project is exempted for creating this deliverable, then select as “Not applicable.” | In Progress Awaiting Sign Off Completed Not Applicable
Preliminary Work Order | Once Project Request is received from IT/Business, PM to follow up with Finance team to secure a Preliminary Work Order by Planning Phase. PM to provide latest status of POW by selecting the drop down. If the Project is not required to have a POW, then select as “Not applicable.” | WO Submitted WO Approval in Progress WO Approved Not Applicable
Full Work Order | Once Preliminary Work Order is assigned to follow up with Finance team to secure a Full Work Order. PM to provide latest status of FOW by selecting the drop down. If the Project is not required to have a FOW, then select as “Not applicable.” | WO Submitted WO Approval in Progress WO Approved Not Applicable

## Slide 7: PROJECT STATUS FORM – JOB AID
IT Project Status Form > Project Info
Fields | Guidelines | Examples/ Options to select
Resources Allocated | Select “Yes” if resources are fully committed to the project and have been assigned to all tasks in project schedule | Yes
 | Select “In Progress” if allocation is in progress and all resources have been identified | In Progress
 | Select “No” if there are insufficient resources or additional resources | No
 | Select “Not Applicable” if project has no resourcing requirement | Not Applicable
Contracting | Drop Down: If Project has contracting requirements, then update the field by selecting the appropriate options. If exempted, then select as “Not Required.” | Contracting from RFP In-Progress RFP Released SOW Signed Not Required
Undivided Joint Interest | If Project is ≥ $500,000, will benefit more than one operating company, and is determined as Undivided Joint Interest, update field by selecting the appropriate option. If exempted, then select as “Not Applicable.” | UJI Form Completed UJI meeting held UJI Approved Not Applicable
ARB Approval | Architecture Review Board Approval is a checkpoint for projects and to be reviewed by ARB Team, update field by selecting the appropriate options. If ARB is waived off, then select as “Not Applicable.” Refer to link for more details | Request an Architect Architect Assigned ARB approved Not Applicable

## Slide 8: PROJECT STATUS FORM – JOB AID
IT Project Status Form > Schedule Details
Fields | Guidelines | Examples/ Options to select
IT Project Phase | Select the current Project Phase from the drop down | 01 - Initiation 02 - Planning 03 - Execution - Requirements 03 - Execution - Design 03 - Execution - Build 03 - Execution - Unit Test 03 - Execution - SIT 03 - Execution - Implement 04 - Closure - Post Implement 04 - Closure - Complete
Baseline Start | This is an automated data entry from the Project schedule and picks up latest baselined start date | 
Finish Date | This is an automated data entry from the Project schedule and picks up finish date | 
Baseline Duration | This is an automated data entry from the Project schedule and picks up latest baselined duration | 
Schedule Duration Performance | This is an automated calculation field based on the below: Less than 10% over baseline schedule Between 10% to 20% over baseline schedule Above 20% over baseline schedule | 
% Complete | This is an automated data entry from the Project schedule and picks up overall % completions for all tasks | 

## Slide 9: PROJECT STATUS FORM – JOB AID
IT Project Status Form > Cost Details
Fields | Guidelines | Examples/ Options to select
Budget Cost | Indicates the Budgeted Cost | This is an automated data entry field from the Project schedule and picks up Budgeted Cost values
Baseline Cost | Indicates the Baseline Cost | This is an automated data entry field from the Project schedule and picks up latest Baselined Cost values
Cost | Indicates Estimate at Completion | This is an automated data entry field from the Project schedule and picks up Estimate at Completion values
Cost Variance | Indicates variance between baseline cost and EAC | This is an automated data entry field which calculates variance between Baseline Cost and Estimate at Completion
Cost Performance | This is one of the key metric for reporting the status of the project with respect to the baseline Cost vs Estimate at completion. | This is an automated calculation field based on the below: Less than 10% over baseline schedule Between 10% to 25% over baseline schedule Above 25% over baseline schedule

## Slide 10: PROJECT STATUS FORM – JOB AID
IT Project Status Form > KPI Details
Fields | Guidelines | Examples/ Options to select
KPI Year | If the Project’s budget is above $100K, Work Order is placed in Service in a particular year e.g., 2018. | 2018
 | If the Project's budget is below $100K | NA
IT KPI Schedule | If a project does not have a second baseline yet, then “IT KPI Schedule" field shall be set to "Not Started" | Not Started
 | PM's assessment on whether a project is going to be delivered on Time or not by the end of project. The field must be updated when there is a KPI schedule status change | On Time
 |  | Late
 | If a program has multiple sub-projects, then KPI On Time for this program shall be set to "NA". But individual sub-projects shall be set to either "On Time", "Late", or "Not Started". | NA
IT KPI Cost | If a project does not have a second baseline yet, then “IT KPI Cost" field shall be set to "Not Started" | Not Started
 | PM's assessment on whether a project is going to be delivered on Budget or not by the end of project. The field must be updated when there is a KPI Cost status change | On Budget
 |  | Not on Budget
 | If a program has multiple sub-projects, then KPI On Cost for this program shall be set to "NA". But individual sub-projects shall be set to either "On Budget", “Not on Budget", or "Not Started". | NA

## Slide 11: PROJECT STATUS FORM – JOB AID
IT Project Status Form > KPI Details
Fields | Guidelines | Examples/ Options to select
IT KPI Quality Year | Update the year when quality assessment was completed for the Project | YYYY
 | If the Project is not involved in Quality Assessment update as ‘NA” | NA
IT KPI Quality | If a project does not have a second baseline yet, then “IT KPI Quality" field shall be set to "Not Started” | Not Started
 | PM's assessment on whether a project is going to be delivered on Quality or not by the end of project. The field must be updated when there is a KPI Quality status change | On Quality
 |  | Not on Quality
 | If a program has multiple sub-projects, KPI Quality for this program shall be set to "NA". If Project is internal & exempted from assessment, then select as “NA.” However, individual sub-projects shall be set to either "On Quality", “Not on Quality", or "Not Started". | NA
IT Project Category | During the Tailoring Guideline Process, determine if the projects are internal or external. If a project is internal, then a quality rating is not needed. Therefore "Quality Rating" field shall be blank | Internal
 | During the Tailoring Guideline Process, determine if the projects are internal or external. If a project is external, then a quality rating shall be entered before completion of project | External
IT Quality Rating | If the Project is internal, then a quality rating is not required | NA
 | If the Project is external, then a quality rating is to be entered post quality survey assessment. | Enter the Quality Rating

## Slide 12: PROJECT STATUS FORM – JOB AID
IT Project Status Form > KPI Details
Fields | Guidelines | Examples/ Options to select
Customer Rater | If the project is an IT internal Project and has no quality assessment then there should not be a customer rater, update as “NA” | NA
 | If the project is external and has quality assessment, which means the rater is someone outside of Ameren IT, provide the names of all external resources involved in providing the Quality Rating. | <Name or Names of the Customer Rater>
Quality Goals | Update field by entering Quality objectives/goals from Project Charter | 
Quality Survey Results | Provide link to all Quality Survey results. | 
Reason if KPI is not Met | If the Project has any of the KPI indicators (Schedule, Cost , Quality) as “not met”, then in these scenarios the PM needs to update reason for miss. Rules to follow while updating the field: Specify which KPI indicator that was not met Specify reasons for the miss | 

## Slide 13
THANK YOU