## Slide 1: ESO November feature deployment schedule
Coding / Development
Integration Testing
PTST/UAT Testing
STAG Testing
Deployment
PERF Testing
Load Testing
11/4/19
11/8/19
10/30/19
UAT Test Scripting
UAT Test Data
11/20/19
11/21/19
Release.Ameren.com Testing
The following are the last possible dates must be ready by for 10/17/19 deployment:
Detail Technical Design
9/10/19
????/19
User Stories Ready
9/6/19
9/25 – start moving code to PTST environment
CSS/API/Web